## SEO Site Migration Checklist
SEO Website Migration Checklist |  |  | Website:
Date:
Note: *This is a general Site Migration checklist. Your list may vary by CMS and other factors.
üBefore Website Launch:
| No. | Task | Responsibility | Status | Comments
| 1 | Crawl the entire website with Screaming Frog to obtain a complete list of site URLs that will be used for setting up and validating 301 redirects. |  | Assigned
| 2 | Provide client or agency with current list of 301s/302s and 404s pages. |  | Assigned
| 3 | Identify all existing 404 error pages. (delete or fix pages) |  | Assigned
| 4 | Benchmark current website and SEO data. Organic traffic, engagement metrics, SEMRush SEO Score, keyword rankings, Google Search Console Data (indexed pages, index errors, sitemap URLs, backlinks, etc.) |  | Assigned
| 5 | New Website URLs. a. 301 redirect old URLs to new URLs. b. Conduct 301 redirect mapping. i. Identify top SEO pages to test and validate 301s. ii. Identify secondary SEO pages to test and validate 301s. iii. New site pages should be descriptive, and SEO optimized and include primary SEO term where applicable. |  | Assigned
| 6 | Update all Internal Links with new URLs. a. Identify issues (broken links) using SEMRush or Screaming Frog. |  | Assigned
| 7 | Canonical URLs (old and new). a. Update all old and new URLs with canonical, self-referencing tags. b. Update all New URLs (canonical tag URL to the preferred URL). |  | Assigned
| 8 | URLs trailing slash (or without the trailing slash) usage – pick one consistent use and use across all web pages, links, canonicals, sitemaps, etc. |  | Assigned
| 9 | Implement NoIndex, Follow tag on the following pages. a. Total Pages = x pages to NoIndex. i. Use tag on each page: <meta name=”robots” content=”noindex, follow”> |  | Assigned
| 10 | Update Robots.txt file for the new site. a. Audit old file to identify any issues blocking search engines from crawling certain directories, pages or resources. b. If new site in including internal site search, please set pages to NoIndex. |  | Assigned
| 11 | Validate is any Schema Markup is being used. a. Ex. Breadcrumb navigation, articles/blogs, events, customer reviews/ratings and FAQs. b. Recommended to used JSON-LD for structured data markup. c. Is Element Three performing markup to the new website? |  | Assigned
üStaging Environment:
| No. | Task | Responsibility | Status
| 12 | Test all 301 redirects are working correctly. a. Run Screaming Frog crawl to validate 301s are correct. |  | Assigned
| 13 | Run SEMRush site audit to identify issues that would harm SEO. a. Address issues and re-run SEMRush scan. |  | Assigned
| 14 | Validate Google Analytics tracking code is on all site pages. |  | Assigned
| 15 | Validate all Meta Data is displayed (Title, Meta Description, and H1 heading). A. Run Screaming Frog scan of site to validate correct page info. |  | Assigned
| 16 | Before site goes live, pause any PPC campaigns that are using updated URLs. a. Unpause campaigns once website is live. |  | Assigned
üPost Website Launch:
| No. | Task | Responsibility | Status | Comments
| 17 | HTTP and HTTPS URLs. a. Validate no site URLs, or internal links are using HTTP. (Screaming Frog scan.) b. All pages should be using HTTPS protocols. |  | Assigned
| 18 | Ensure custom 404 error page is live on the new site. a. Use Screaming Frog scan to find 404 pages. (Include GA data.) |  | Assigned
| 19 | Validate all Meta Data is displayed (Title, Meta Description, and H1 heading) are carried over from previous page configurations. a. Use Screaming Frog scan data to validate correct info. |  | Assigned
| 20 | Validate Canonical URLs (old and new). a. Update all old and new URLs with canonical, self-referencing tags. b. Update all New URLs (canonical tag URL to the preferred URL). c. Analyze SEMRush and Screaming Frog data to validate. |  | Assigned
| 21 | Update Sitemaps and submit through Google Search Console (GSC). a. *Keep the old XML sitemap page (with original URLs) – do not delete this page. b. **Create New XML sitemap and only include top SEO performing pages. c. Validate GSC data is tracking properly. d. Review issues and errors logs. |  | Assigned
| 22 | Validate Google Analytics (GA & G4) are reporting correctly. a. *Preserve any prior tracking scripts, codes, goals, etc. b. Update notation of when new site is live within GA. |  | Assigned
| 23 | Validate robots.txt file is not blocking high-value SEO pages and is setup correctly. a. Review Google Search Console for pages being blocked from indexing. |  | Assigned
| 24 | Validate is any Schema Markup is being used. a. Ex. Breadcrumb navigation, articles/blogs, events, customer reviews/ratings and FAQs. b. Recommended to used JSON-LD for structured data markup. c. Is Element Three performing markup to the new website? |  | Assigned
| 25 | Update all PPC campaigns to the new URLs. (where applicable). a. Validate all campaigns have been updated to point to the new site URLs. b. Monitor campaign performance and look for any negative trending. |  | Assigned
| 26 | Update all email campaigns, Social Media, and other web channels using the updated URLs. |  | Assigned
| 27 | Update Google My Business and Bing Places with updated URLs (where applicable.) |  | Assigned
| 28 | Update backlinks (of your high-value SEO pages.) a. Reach out to website owners to update links to the new URLs. b. Validate and test that updated links are working correctly. c. Monitor backlinks trending through GSC and SEMRush. |  | Assigned
| 29 | Check Google Search Console page experience metrics to see if page speed performance issues exist. a. Validate also through GTMetrix, Google Page Speed Insights, or measurement tools. |  | Assigned
| 30 | Monitor Google site indexed pages (through Google Search Console). a. Baseline before new site launch. b. Baseline post site launch. c. Identify issues and troubleshoot. |  | Assigned
| 31 | Re-Crawl the entire site (with Screaming Frog) to identify 404s and broken 301 redirects. a. Identify all non-200 response code URLs. b. Troubleshoot and fix all 404s, 302s, and 5XX codes. f. Identify 404s (determine if the page was intentionally removed) or 301 redirect that needs to be set up correctly. c. Identify broken images d. Missing meta tags e. Canonical tag issues g. Check external URLs. (These URLs should not return 301s or 404s.) h. Also, check Google Analytics Organic / Landing Pages / 404 error pages. |  | Assigned
üAfter Successful Website Launch:
| No. | Task | Responsibility | Status | Comments
| 32 | Monitor Google Analytics for organic traffic trends. a. Confirm goals and events are tracking correctly in G4 Google Analytics. |  | Assigned
| 33 | Monitor Google Search Console for changes and trends in website indexation errors, total pages indexed, and impressions and clicks. |  | Assigned
| 34 | Update SEMRush Position Tracking to include new pages and SEO terms to track and measure. |  | Assigned
| 35 | Continue to reach out to website owners to update page URLs to the new URLs. a. This will help mitigate decreases in links to the site.com website. |  | Assigned
| 36 | SEMRush and other SEO Audit tools. a. Conduct other site audits to find technical SEO issues and problems that need fixing. |  | Assigned

## Settings
Responsbility | Task Status
company a | Assigned
company b | In Process
company c | Help
company d | In Review
Done